## 📖 Process Guide
📖 BUGABOO LANDSCAPING LTD — CONSTRUCTION PROCESS GUIDE (SOP)
🟢 PHASE 1: ONBOARDING
1 | Send pre-construction consult email to prospect | Use email template to gather: scope, budget range, timeline, site photos
2 | Enter client details in system & assign Operator (OO) | Dashboard sheet → Project Status = 'Lead'
3 | Schedule initial consultation meeting | All divisions (irrigation, treecare) should coordinate if multi-scope
🟡 PHASE 2: QUOTING & DESIGN
4 | OO meets client — capture vision, take measurements | Bring measuring tape, camera, site sketch pad
5 | Complete TAKEOFF SHEET (📊 Takeoff & Quote tab) | Fill in all quantities, material costs, labour & machine hours, mobilization
6 | Review quote internally before sending | Check: margin ≥ 35%, all sections filled, notes added
7 | Generate Customer Quote (📄 Customer Quote tab) | Transfer line items; review for client-friendly language
8 | Send quote — follow up within 3 business days | Update Dashboard → Status = 'Quoted'
9 | Obtain signed acceptance + 50% deposit | Update Dashboard → Status = 'Deposit Received'
🔵 PHASE 3: PRE-CONSTRUCTION (1–4 weeks)
10 | Apply for permits; order locates | Update Dashboard timeline — Est. Start date for each phase
11 | Order materials with lead-time in mind | Log in 🧾 Material Log tab — match to takeoff budget
12 | Confirm OO schedule and project start date | Notify client of start date + any factors that may affect timeline
🟠 PHASE 4: CONSTRUCTION
13 | Demolition (1–2 days) | Log labour hours daily in ⏱️ Labour & Machine Log
14 | Grading & Drainage (1–2 days) | Record dump loads, fuel costs in Material Log (category: Mobilization)
15 | Irrigation install (1–2 days) | Cross-check against takeoff hours — flag overages immediately
16 | Hardscape install (variable) | Photo-document each phase for warranty & customer completion package
17 | Planting / Sod (1–2 days) | Confirm soil, sod, plant quantities match material log
18 | Final touches / cleanup (1–2 days) | Site photos — before and after required
🔴 PHASE 5: PROJECT COMPLETION
19 | Final walkthrough with client — punchlist | Address all issues before final invoice
20 | Prepare completion package | Before/after photos, watering instructions, warranty document, care guide
21 | Send final invoice (remaining 50%) | Update Dashboard → Status = 'Punch List' → 'Complete'
22 | Collect Google/Facebook review | Send review link immediately after completion call
🟣 PHASE 6: RECONCILIATION
23 | Reconcile all material receipts vs. takeoff budget | 🧾 Material Log — ensure every receipt is logged
24 | Reconcile all labour & machine hours vs. estimate | ⏱️ Labour & Machine Log — total vs. takeoff hours
25 | Complete Project P&L (🔄 Reconcile P&L tab) | Enter actual invoiced revenue; review variances
26 | Document lessons learned | Note: any items consistently over/under budget for future estimating accuracy
27 | Archive project & close in system | Change Dashboard → Status = 'Complete'

## 📋 Dashboard
🌿 BUGABOO LANDSCAPING LTD — PROJECT MANAGEMENT SYSTEM
Project Name: |  |  |  | FINANCIAL SUMMARY
Project Address: |  |  |  | Quote / Contract Value |  | 0
Client Name: |  |  |  | Total Est. Direct Cost |  | 0
Client Phone: |  |  |  | Gross Profit $ |  | 0
Client Email: |  |  |  | Gross Margin % |  | 0%
Operator (OO):
OO Phone: |  |  |  | ACTUAL (Reconciled)
Project Start: |  |  |  | Actual Revenue |  | 0
Est. Completion: |  |  |  | Actual Total Cost |  | 0
Project Status: |  |  |  | Actual Gross Profit |  | 0
|  |  |  | Actual Margin % |  | 0%
PROJECT TIMELINE & MILESTONES
Phase | Description | Est. Start | Est. End | Actual Start | Actual End | Status
Permitting / Locates
Demolition
Grading & Drainage
Irrigation
Hardscape
Planting
Final Touches / Cleanup
PROJECT NOTES & COMMUNICATION LOG
Note 1:
Note 2:
Note 3:
Note 4:
Note 5:
Note 6:

## 📊 Takeoff & Quote
🌿 BUGABOO LANDSCAPING LTD — PROJECT TAKEOFF & QUOTE
Client Name: |  |  |  |  | Project Name:
Address: |  |  |  |  | Operator (OO):
Phone: |  |  |  |  | Quote Date:
Email: |  |  |  |  | Quote #:
Project Description:
PRICING ASSUMPTIONS ¦ Blue = Input ¦ E8 = Internal Labour Cost ($30) ¦ P8 = Client Bill Rate ($90 - trucks/trailers/WCB/insurance/overhead) | [14 empty] | 0 | 0
Material Markup % | 25% | Internal Labour ($/hr) | 30 | Machine Rate ($/hr) | 145 | Fuel Cost/Load | 45 | Dump Fee/Load | 120 | Delivery Fee | 150 | Desired Margin % | 35% |  | 0 | 0
# | Scope / Line Item | Unit | Qty | Material Cost/Unit | Total Material | Labour Hours | Labour Cost (Internal) | Machine Hours | Machine Cost | Mobiliz. & Other | LINE TOTAL (Cost) | Markup Added | Quoted Line Price | Notes | 0 | 0
🔨 DEMOLITION & REMOVAL | [14 empty] | 0% | 0%
1 | Remove & dispose existing soil |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
2 | Remove & dispose boulders / rocks |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
3 | Remove existing hardscape |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
4 | Haul-away / dump loads |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
Subtotal — 🔨 DEMOLITION & REMOVAL | [10 empty] | 0 |  | 0
🏔️ GRADING & DRAINAGE
1 | Spread, grade & compact |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
2 | Fine grading |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
3 | Drainage swale / French drain |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
4 | Topsoil supply & spread |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
Subtotal — 🏔️ GRADING & DRAINAGE | [10 empty] | 0 |  | 0
💧 IRRIGATION
1 | Irrigation design & permits |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
2 | Main line & lateral trenching |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
3 | Heads, valves & controller |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
4 | Startup & testing |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
Subtotal — 💧 IRRIGATION | [10 empty] | 0 |  | 0
🧱 HARDSCAPE
1 | Patio – excavation & base |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
2 | Patio – stone / pavers supply & lay |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
3 | Retaining wall – excavation & base |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
4 | Retaining wall – block supply & build |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
5 | Walkway / steps |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
6 | Edging |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
Subtotal — 🧱 HARDSCAPE | [10 empty] | 0 |  | 0
🌱 SOFTSCAPE & PLANTING
1 | Sod – supply & install |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
2 | Loam / premium soil supply |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
3 | Shrubs & perennials – supply & plant |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
4 | Landscape fabric supply & install (weed suppression) |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
6 | Seed & starter fertilizer |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
Subtotal — 🌱 SOFTSCAPE & PLANTING | [10 empty] | 0 |  | 0
🪵 STRUCTURES
1 | Fence / gate supply & install |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
2 | Deck / pergola / arbor build |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
3 | Planter boxes build |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
4 | Privacy screen |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
Subtotal — 🪵 STRUCTURES | [10 empty] | 0 |  | 0
🚛 MOBILIZATION & OVERHEAD
1 | Equipment mobilization |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
2 | Fuel – project total |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
3 | Dump fees – total |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
4 | Material delivery fees |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
5 | Permits & locates |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
6 | Contingency / misc |  |  |  | - |  | - |  | - |  | 0 | 0 | 0
Subtotal — 🚛 MOBILIZATION & OVERHEAD | [10 empty] | 0 |  | 0
[12 empty] | TOTAL ESTIMATED DIRECT COST |  |  | 0
[12 empty] | TOTAL QUOTED PRICE (incl. markup) |  |  | 0
[12 empty] | Desired Margin Check – Target Revenue |  |  | 0
[12 empty] | Gross Profit ($) |  |  | 0
[12 empty] | Gross Margin % |  |  | 0%
[12 empty] | Margin vs. Target |  |  | ⚠️ BELOW TARGET
🔵 Blue cells = Enter your values ¦ ⚫ Black cells = Auto-calculated ¦ 🟡 Yellow = Input fields

## 📄 Customer Quote
BUGABOO LANDSCAPING LTD
📞 403-283-7843 ¦ ✉️ Support@bugaboolandscaping.com ¦ 🌐 www.bugaboolandscaping.com
PREPARED FOR: |  | QUOTE DETAILS
Client Name: | 0 | Quote #: | 0
Address: | 0 | Date: | 0
Phone: | 0 | Valid Until:
Email: | 0 | Operator: | 0
PROJECT DESCRIPTION
0
SCOPE OF WORK | UNIT | QTY | PRICE
Subtotal |  |  | 0
GST (5%) |  |  | 0
TOTAL |  |  | 0
⚠️ A 50% deposit is required to secure your project start date.
Note: This estimate is valid for 30 days. Final costs may vary due to unforeseen site conditions.
WARRANTY SUMMARY
✔ General Workmanship: 2 years
✔ Stone Patios & Retaining Walls: 2 years against major shifting/settling
✔ Woodwork (decks, fences, pergolas): 2 years structural defects
✔ Irrigation: 2 years parts & labor (proper winterization required)
✗ Plants, sod, shrubs, trees: No warranty (living material – proper aftercare required)
ACCEPTANCE & AUTHORIZATION
I/We hereby accept this proposal and authorize Bugaboo Landscaping Ltd to proceed.
Client Signature: ___________________________ |  | Date: _______________
Print Name: ___________________________

## 🧾 Material Log
🧾 MATERIAL PURCHASE LOG — Track Every Receipt Against Budget
Date | Supplier / Vendor | Description / Item | Category | Qty | Unit Cost | Total Cost | Budget (Takeoff) | Over/Under | Invoice # | Notes
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
[5 empty] | - |  | -
TOTAL MATERIAL SPEND |  |  |  |  | 0

## ⏱️ Labour & Machine Log
⏱️ LABOUR & MACHINE TIME LOG — Track Hours vs. Budget
Date | Worker / Operator | Task / Phase | Labour Hrs | Internal Rate ($/hr) | Internal Labour Cost | Machine Hrs | Machine Rate | Machine Cost | Notes | Labour Billed ($90/hr)
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  |  | 30 | - |  | 145 | - |  | -
|  |  | 0 | 30 | 0 | 0 | 145 | 0 |  | 0
TOTALS |  | 0 |  | 900 | 0 |  | 4350

## 🔄 Reconcile P&L
🔄 PROJECT RECONCILIATION & PROFIT & LOSS
REVENUE
Line Item | Quoted | Actual (Invoiced) | Variance $ | Variance %
Project Revenue (excl. GST) | 0 |  | 0
COST OF GOODS SOLD (DIRECT COSTS) |  |  |  |  | 0
Cost Category | Quoted Cost | Actual Cost | Variance $ | Variance % | 0
Materials | 0 | 0 | - | 0% | 0
Labour | 0 | 0 | - | 0% | 0%
Equipment / Machine | 0 | 0 | - | 0%
Mobilization (Fuel, Dump, Delivery) | 0 |  | - | 0%
Sub-Contractors |  |  | - | 0%
Other Direct Costs |  |  | - | 0%
TOTAL DIRECT COST | 0 | 0 | 0 | 0%
OVERHEAD & INDIRECT COSTS
Category | Quoted | Actual | Variance $ | Variance %
Warranty Reserve |  |  | 0 | 0%
Insurance allocation |  |  | 0 | 0%
Admin / Office allocation |  |  | 0 | 0%
PROJECT P&L SUMMARY
| Quoted | Actual | Variance $ | Variance %
Revenue | 0 | 0 | 0 | 0%
(-) Direct Costs | 0 | 0 | 0 | 0%
(-) Overhead | 0 | 0 | 0 | 0%
NET PROFIT / LOSS | 0 | 0 | 0 | 0%
NET MARGIN % | 0% | 0%
📊 LABOUR RATE ANALYSIS
Labour Item | Estimated | Actual | Variance $ | Notes
Labour Hours (Total) | 0 | 0 | 0 | hrs over/under estimate
Our Labour Cost (@ $30/hr) | 0 | 0 | 0 | Actual cost to Bugaboo
Labour Billed to Client (@ $90/hr) | 0 | 0 | 0 | Billed to client for labour
Labour Overhead Contribution | 0 | 0 | 0 | Trucks/WCB/insurance/overhead recovered